## Slide 1
Capital Improvement Program
June 22, 2020
Citizen Bond Oversight Committee
Update

## Slide 2
Welcome and Introductions
Review and Approve 02/24/2020 Meeting Minutes
CIP Construction Program
  Overview, Mr. Lacy Hampton, Interim Assoc. Vice Chancellor of G.O. Bond CIP
  SPC – Dr. Adena W. Loston, President
  SAC – Dr. Robert Vela, President
  NVC – Dr. Ric Baser, President
  PAC – Dr. Robert Garza, President
  NLC – Dr. Veronica Garcia, President
  ETC – Mr. Xavier Urrutia, Interim Vice Chancellor of Economic Workforce and Development
  CIP Technology Bond Overview
    Dr. Tom Cleary, Vice Chancellor of Planning Performance and Information Systems
  Report on Construction Manager’s SMWVBE Subcontracting Plans
Schedule Next Meeting and Closing Comments
Agenda

## Slide 3: CIP Construction Program

## Slide 4
CIP Funding Breakdown
COLLEGE | GENERAL OBLIGATION BONDS
Northeast Lakeview College | $42M
Northwest Vista College | $69M
Palo Alto College | $66M
San Antonio College & First Responder’s Academy | $83M
St. Philip’s College & Southwest Campus | $82M
Educational Training Centers | $69M
Safety and Security: Redundant Dispatch Center | $3M
Information Technology | $25M
Real Estate (N 281 & PAC) | $11M
TOTAL | $450M
Construction Projects

## Slide 5
Areas of Investment
Expanding training and preparing for high growth demands
Broadening information technology service demands
One-stop shop for student enrollment and support
Health Bioscience
STEM
Labs
Advance
Manufacturing
Finance
Growth
Information
Technology
Student
Support
Increasing emphasis on education in high demand high growth business, science, technology, engineering and mathematics fields
Centers of Excellence

## Slide 6
CIP Funding
$450M General Obligation Bond Election – Passed May 2017
  No tax rate increase necessary
  Bonds were originally planned to be sold in 3 tranches
    Fall 2017 Issued $173M; and planned Fall 2019 ($169M); Fall 2021($108M)
    Based on current cash flow projections expect to issue up to $225M of bonds in Jan.2021 and remaining amount Jan. 2022
Project Costs determined during 2016, experiencing annual cost inflation of 4.46%
In May 2019 ACD Board approved issuance of $50M in Maintenance Tax Notes (MTN) to help with renovation projects and projects’ furniture, fixture and equipment, freeing up some capacity in the G.O. bonds. On May 2020, the Board approved the “Rebalancing” of the G.O. Bonds and MTN funding for each college campus
TOTAL CIP BOND FUNDING: $500M ($450M G.O. Bonds + $50M MTN)

## Slide 7
PROJECT STATUS | COUNT
Construction Complete | 1
In Construction | 8
GMP Approved | 4
GMP Within 3 Months | 3
In Design | 8
Total | 24
Bond Projects by the Numbers
Notes: GMP within 3 month: .; 1 PAC: Nat Gym SPC Bowden 3 Auto Body NVC: 4 STEM
GMP approved 1 SAC Fletcher ETC – 2 WETC
In Design – SAC: 1 Childcare; 2 chance new bldg; 3 FRA; 4 McAllister; PAC: 5 PPI and 6 Multipurpose NLC: 7Stem NVC: 8 Cypress ETCS: 9 NWETC and 10 SETC
In Construction: SPC –THCA & Norris SAC: Garage; PPI, NVC: Welcome Center & Garage & PPI
Construction Complete: Redundant SPC SWC

## Slide 8
Type | G.O. Bond Funds | Status
New | $3 M | Completed
Redundant Dispatch Center
Completed Project

## Slide 9: St. Philip’s College
Dr. Adena W. Loston, President

## Slide 10
G.O. Bonds $82 Million
Maintenance Tax Note $10.99 Million (primarily Norris Renovation)

## Slide 11
SPC Updated Budget Targets With MTN Impact
NTP Issued
08/11/2020

## Slide 12
List of Projects
St. Philip’s College – Tourism, Hospitality, and Culinary Arts (THCA)
Welding and Auto Body Facility March 2020
Bowden Building (NTP Issued) May 2020
GMP Approved (2)
College Campus | Orig. GO Bond | Allocation Of MTN | Other Funding | Revised GO Bond Plan | Total
SPC | $82M | $10.99M | $5.07M | $82M | $98.06M
Tourism, Hospitality, and Culinary Arts (THCA)
In Construction: Norris Tech. Building Renov.
Approaching Substantial Completion
In Construction (2)

## Slide 13
SPC – Tourism, Hospitality, and Culinary Arts (THCA)
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$30M | $1.02M (Inst. Budget) | $2.18M | $33.2M | $28.05M | $5.15M
Project Statistics:
Architect: Page
CMAR: Skanska USA Building, Inc.
GMP: $28,200,000
GMP Approved: 12.11.18
Building Square Footage: 62,128 sf (4 stories)
Classrooms: 7 Classrooms. Labs: 5 Teaching Kitchen Labs, 2 Full Commercial Projection Kitchen Labs
Special Purpose Areas: 100 Seat Tiered Lecture Hall, Hospitality Area (Mock Hotel Space), 2 Public Restaurants
Construction Start: February 2019
Target Completion: August 2020
Academic Term Opening: Fall 2020
CMAR SMWVBE % Committed: 25%
Construction % Complete: 90%
SUBSTANTIAL COMPLETION
Notes: ICON THEME: Growth
Tourism Hospitality and Culinary Arts
Original $30M
Rebalance $--
Other funding $1.4M
MTN $2.1M
SMWVBE: 15%

## Slide 14
SPC – Tourism, Hospitality, and Culinary Arts (THCA)
SUBSTANTIAL COMPLETION

## Slide 15
SPC – Tourism, Hospitality, and Culinary Arts (THCA)
SUBSTANTIAL COMPLETION

## Slide 16
SPC – Tourism, Hospitality, and Culinary Arts (THCA)
SUBSTANTIAL COMPLETION

## Slide 17
SPC – Tourism, Hospitality, and Culinary Arts (THCA)
SUBSTANTIAL COMPLETION

## Slide 18
SPC – Tourism, Hospitality, and Culinary Arts (THCA)
SUBSTANTIAL COMPLETION

## Slide 19
SPC – Tourism, Hospitality, and Culinary Arts (THCA)
SUBSTANTIAL COMPLETION
Time Lapse video: https://skanska.box.com/s/bxggptw82ukok7q726rclz4btorizflr
Render video: https://skanska.app.box.com/s/x6xizesettq64058e2aq03bwgw6mop6c

## Slide 20
SPC – Norris Tech. Bldg. Renov.
Project Statistics:
Architect: Pfluger
CMAR: Skanska USA Building, Inc.
GMP, as Amended: $19,286,081
GMP Approved: 12.11.18, Amended on 10.22.19
Building Square Footage: 64,080 sf + 6,911sf = 70,991sf (4 stories)
Classrooms: 7 General , 10 Computer, 1 Open Lab
Labs: Tutoring & Technology Center, Rose Thomas Writing Center Special Purpose Areas: Information Technology Dept, Communications & Learning Dept, 6 Student Lounge/Study areas
Construction Start: July 2019
Target Completion: November 2020
Academic Term Opening: Spring 2021
CMAR SMWVBE % Committed: 25%
Construction % Complete: 70%
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$14.88M | $1.42 | $8.81M | $25.11M | $15.98M | $9.3M
IN CONSTRUCTION
Notes: ICON THEME: Information Technology; Growth
Original $22M
Rebalance $15.5$
GMP amend Added $2,506,081
Original GMP amount 16,780,000 approved on 12/11/18
SMWVBE: 14.5%

## Slide 21
SPC – Norris Tech. Bldg. Renov.

## Slide 22
SPC – Norris Tech. Bldg. Renov.

## Slide 23
SPC – Norris Tech. Bldg. Renov.
IN CONSTRUCTION

## Slide 24
SPC – Norris Tech. Bldg. Renov.

## Slide 25
SPC – Norris Tech. Bldg. Renov.

## Slide 26
SPC – Norris Tech. Bldg. Renov.

## Slide 27
SPC – Norris Tech. Bldg. Renov.

## Slide 28
SPC SWC - Welding and Auto Body Facility
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$23.12M | $1.96M (Inst. Budget) | $- | $25.07M | $1.2 | $23.87M
Project Statistics:
Architect: WestEast Design Group
CMAR: Guido Construction Company, Inc.
GMP: $19,861,680
GMP Approved: 03.17.2020
Building Square Footage: 62,093 sf (1.5 stories)
Classrooms and Labs: 1 Large Multipurpose 3 Computer; 6 General; Labs: 2 Large Instructional Labs (Welding & Auto Body); 120 Welding Stations; 32 Auto Body Welding Stations; 2 Paint Booths; 1 Double Bay Prep
Est. Construction Start: July 2020
Est. Target Completion: March 2022
Est. Academic Term Opening: Spring 2022
CMAR SMWVBE % Committed: 25%
Construction % Complete: GMP Approved
GMP Approved
Notes: ICON THEME: Advanced Manufacturing; Growth
Original $20M
Rebalance $22.4
Other funding $1.4M
MTN $
SMWVBE: 15%

## Slide 29
siteplan
Located at Quintana Road and Harmon Ave next to existing Building 8.
The new building will replace the existing older facility on the campus increasing square footage from 33,254sf to 62,093sf
SPC SWC - Welding and Auto Body Facility
GMP Approved

## Slide 30
Level 1
2 Large Instructional Laboratories
Welding Lab features
  120 Welding stations
Autobody Collision features
  32 Welding stations
  2 paint Booths
  1 Double Bay Prep Booth
Remaining Floor Area
Administrative spaces
Faculty Offices
Support Spaces
SPC SWC - Welding and Auto Body Facility
GMP Approved

## Slide 31
Level 2
3 Computer Classrooms (seating 32)
6 General Classrooms (seating 32)
Large Multipurpose Room (seating up to 100)
2 Informal Study Areas
SPC SWC - Welding and Auto Body Facility
GMP Approved

## Slide 32
SPC - Bowden Building
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$14M | $0.68M (Inst. Budget) | $- | $14.68M | $0.50M | $14.18M
Project Statistics:
Architect: Page
CMAR: Skanska USA Building, Inc.
GMP: $10,806,501
GMP Approved: 05.19.2020
Building Square Footage: 24,870 sf (2 stories)
Classrooms and Labs: General and Computer
Labs: 3 Tradition 2 Collaborative Networking Labs;
Accounting and Technology Labs
Special Purpose Areas: Artemisia Bowden Bust
And Portrait, VITA (Volunteer Income Tax
Assistance) Center
Est. Construction Start: June 2020
Est. Target Completion: August 2021
Est. Academic Term Opening: Fall 2021
CMAR SMWVBE % Committed: 25%
Construction % Complete: NTP Proceed
GMP Approved/NTP
Notes: ICON THEME: Finance; Information Technology, and Growth
Original $10M
Rebalance $14M
Other funding $.7M
MTN $-
SMWVBE: %

## Slide 33
The replacement Bowden Building will be located at what will become the new main entry to the campus off of MLK Drive.
Building Site Plan
Campus Site Plan
SPC - Bowden Building
GMP Approved/NTP

## Slide 34
SPC - Bowden Building
GMP Approved/NTP

## Slide 35
Main Lobby:
Bright / Open Space
Open Stair to Second Floor
Open Glazing to VITA and Dean Reception Areas
Museum-like Clean / Modern Aesthetic
Artemisia Bowden Bust and Portrait / Heritage Tree
High Tech Video Display Wall
SPC - Bowden Building
GMP Approved/NTP

## Slide 36
First Floor
Main Reception Lobby
VITA Tax Assistance Center
General Classroom
Computer Classroom
Faculty Office Suite
SPC - Bowden Building
GMP Approved/NTP

## Slide 37
Second Floor
3 Networking Computer Labs (Traditional Layout)
2 Networking Computer Labs (Collaborative Layout)
Dedicated Server Rooms
Accounting Lab
Technology Integration Lab
Informal Student Study Area
SPC - Bowden Building
GMP Approved/NTP

## Slide 38: San Antonio College
Dr. Robert Vela, President

## Slide 39
G.O. Bonds (per Election Flyer): $83 Million
Maintenance Tax Notes (approved 5/2019) $11.10 Million (Fletcher Renovation)
Chance Renov.: Fin.
NEW Science Bldg.
Garage/Street Work
Childcare Center
Deferred $4.5M

## Slide 40
SAC Updated Budget Targets With MTN Impact
NTP Issued
10/2021

## Slide 41
List of Projects
San Antonio College – Parking Garage / San Pedro Scope Improvements
Physical Plant
Parking Garage/San Pedro Scope
Fletcher Administration Center Renov.
In Construction (3)
Childcare/Santikos Multipurpose Center
Chance Renov.
New Science Building (9 additional labs)
First Responders Academy
McAllister Renov. - Deferred
Future (4)
College Campus | Orig. GO Bond | Allocation Of MTN | Other Funding | Revised GO Bond Plan | Total
SAC | $83M | $11.10M | $2.26M | $83M | $96.36M

## Slide 42
Project Statistics:
Architect: O’Connell Robertson
CMAR: J.T. Vaughn Construction, LLC
GMP, as Amended: $20,771,712
GMP Approved: 12.11.18, Amended on 05.19.2020
Parking Spaces: 732 (5 levels)*
Net Add of Parking Spaces: 355*
Added Scope: San Pedro Street Improvements
Construction Start: July 2019
Target Completion: September 2020
Academic Term Opening: Spring 2021
CMAR SMWVBE % Committed: 24%
Construction Complete: 60%
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/2020 | ESTIMATE TO COMPLETE
$20.31M | $0.47 | - | $20.77M | $10.70M | $10.07M
IN CONSTRUCTION
* Removed 1 level, due to re-evaluation of campus parking requirements
SAC – Parking Garage/Added Scope San Pedro Improvements
Notes: ICON THEME: Growth and Student Support
Original $16M
Rebalance $19M
40% materials are already purchased
SMWVBE: 39.56%

## Slide 43
IN CONSTRUCTION
SAC – Parking Garage/Added Scope San Pedro Improvements

## Slide 44
IN CONSTRUCTION
SAC – Parking Garage/Added Scope San Pedro Improvements

## Slide 45
Why San Pedro Street Improvements?
Required added scope by City Of San Antonio.
Determined by Traffic Impact Analysis.
Required to obtain Certificate of Completion
SAC – Parking Garage Added Scope San Pedro Improvements

## Slide 46
IN CONSTRUCTION
SAC – Parking Garage/Added Scope San Pedro Improvements
W. EVERGREEN ST.
W. PARK
W. MYRTLE
MAVERICK

## Slide 47
Improvements from W Evergreen St. to 400ft past W Myrtle St.
Removal and re-installation of concrete sidewalks
Addition of concrete medians for traffic turn lanes at W Park and Scobee Loop Exit onto San Pedro
Traffic signal revisions
  underground electrical at West Park due to deletion of W Park Street into campus.
  Includes underground electrical at W Myrtle due to the addition of Scobee Loop exiting onto San Pedro Ave
Coordination with CPS for Power requirements
Storm drain utilities at exit from Scobee Loop onto San Pedro Ave
Temporary traffic lane closures and re-routing to accommodate construction
Pavement markings, signage, and ADA crossings
SAC – Parking Garage Added Scope San Pedro Improvements

## Slide 48
SAC – Physical Plant
Project Statistics:
Architect: O’Connell Robertson
CMAR: J.T. Vaughn Construction, LLC
GMP: $2,820,596
GMP Approved: 12.11.18
Academic Term Opening: Spring 2021
Target Construction Start: July 2019
Target Completion: September 2020
Construction % Complete: 85%
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/2020 | ESTIMATE TO COMPLETE
$2.64M | - | - | $2.64M | $1.7M | $0.94M
IN CONSTRUCTION
Current scope covers no expansion to building/equipment, only utility connections from plant to new buildings.
Estimated savings to occur on project reducing the GMP
Notes: ICON THEME: Growth
Original $4.5
Rebalance $2.6M

## Slide 49
SAC – Fletcher Admin. Center Renov.
Project Statistics:
Architect: O’Connell Robertson
CMAR: J.T. Vaughn Construction, LLC
GMP: $18,552,118
GMP Approved: 1.21.20
Building Square Footage: 60,039 sf
Classrooms and Labs: Tino & Millie Duran Welcome Center; Multipurpose Room; Outreach Recruitment; Testing & Advising; Admissions & Records; Technology Center; Student Lounge, Technology Center & Café; Business Office & Financial Aid. Labs: Testing Labs
Est. Target Construction Start: June 2020
Est. Target Completion: October 2021
Est. Academic Term Opening: Spring 2022
CMAR SMWVBE % Committed: 24%
Construction % Complete: 2%
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$10.31M | $- | $11.10M | $21.41M | $1.28M | $20.13
In Construction
Notes: ICON THEME: Student Support, Finance; and Growth
Original $20M
Rebalance $10.3M
SMWVBE: %

## Slide 50
Building Site Plan
N. MAIN AVENUE
W. EVERGREEN
SAC – Fletcher Admin. Center Renov.
In Construction

## Slide 51: New Main Entry
Fletcher Student Success Administration Building – New Main Entry
Ramp Accessibility
Outdoor Learning Area
Patio Seating
Fletcher – Current
SAC – Fletcher Admin. Center Renov.
In Construction

## Slide 52
Southeast Aerial View
East Aerial View
SAC – Fletcher Admin. Center Renov.
In Construction

## Slide 53
1st Floor/Basement
Admissions & Records
Assessment & Advising Center
Testing Center
Outreach Recruitment
Multipurpose Event Room
SAC – Fletcher Admin. Center Renov.
In Construction

## Slide 54
2nd Floor
Tino & Millie Duran Welcome Center
Student Lounge
Student Café
Student Technology Center
Financial Aid
Business Office
Student Orientation Center

## Slide 55
3rd Floor
Offices
Multipurpose Conference Rooms
In Construction

## Slide 56: Northwest Vista College
Dr. Ric Baser, President

## Slide 57
G.O. Bonds (per Election Flyer): $69 Million
Maintenance Tax Notes (approved 5/2019) $10 Million (Cypress Renovation)
Garage
Welcome Center
Cypress Renovation
Utilities Connections Only

## Slide 58
Parking Garage and Welcome Center $26M project was split into two structures next to each other
NVC Updated Budget Targets With MTN Impact
NTP Issued
Notes: Red dot visually of the construction and those to come in future.
Target Completion dates are past (Feb and March – shouldn’t that be future?)

## Slide 59
College Campus | Orig. GO Bond | Allocation Of MTN | Other Funding | Revised GO Bond Plan | Total
NVC | $69.0M | $10.0M | $ | $69.0M | $79.0M
List of Projects
Northwest Vista College – STEM Center of Excellence
STEM Center of Excellence (NTP Issued) April 2020
Physical Plant
Texas Ash Parking Garage
Desert Willow Welcome Center
In Construction (3)
GMP Approved (1)
Cypress Cultural Center of Excellence Renov.
Future (1)

## Slide 60
NVC – Desert Willow Welcome Center
Project Statistics:
Architect: Alamo Architects
CMAR: SpawGlass Contractors, Inc.
GMP, as Amended: $13,855,466
GMP Approved: 12.11.18, Amended on 10.22.19
Building Square Footage: 53,157 sf
Student Resources: Vista Central Admissions & Records, Business Services, Financial Aid, Wellness, Advising & Testing
Construction Start: October 2019
Target Completion: July 2020
Academic Term Opening: Summer 2020
CMAR SMWVBE % Committed: 25%
Construction Complete: 90%
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$17.87M | $- | $1.82M | $19.69M | $14.9M | $4.7M
SUBSTANTIAL COMPLETION
Notes: ICON THEME: Student Support, Information Technology, Growths
Original $17 M
Rebalance $19M
Estimate to complete is the difference between total GO Bond less expenses.
Original GMP amount $14,045,605 deducted ($190,139.00)
Original GMP approve date 12.11.18
SMWVBE: 17%
If there is amendment, make to sure to include in the Stats
Also include amend date
If Academic its about the students
If its welcome center –
Place the Icons near the name.
Remove special purposes
Expenses are showing the first buckets actuals.

## Slide 61
NVC – Desert Willow Welcome Center

## Slide 62
NVC – Desert Willow Welcome Center
1st Floor Lobby Atrium

## Slide 63
NVC – Desert Willow Welcome Center
Vista Central Admissions and Records
Wellness

## Slide 64
NVC – Texas Ash Parking Garage
Project Statistics:
Architect: Alamo Architects
CMAR: SpawGlass Contractors, Inc.
GMP, as Amended: $8,360,243
GMP Approved: 12.11.18, Amended on 10.22.19
Parking Spaces: 451 (4 Levels)
Net Add of Parking Spaces: 451
Construction Start: October 2019
Target Completion: July 2020
Academic Term Opening: Summer 2020
CMAR SMWVBE % Committed: 25%
Construction % Complete: 65%
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 2/20/20 | ESTIMATE TO COMPLETE
$9.76M | - | - | $9.76M | $8.28M | $1.48M
IN CONSTRUCTION
Notes: ICON THEME: Growth
Original $9 M
Rebalance $9.8M
Estimate to complete is the difference between total GO Bond less expenses
Original GMP amount $7,968,892 added $391,351.00
Original GMP approved 12.11.18
SMWVBE: 22%

## Slide 65
NVC – Texas Ash Parking Garage
IN CONSTRUCTION
Notes: ICON THEME: Growth
Original $9 M
Rebalance $9.8M
Estimate to complete is the difference between total GO Bond less expenses
Original GMP amount $7,968,892 added $391,351.00
Original GMP approved 12.11.18
SMWVBE: 22%

## Slide 66
NVC – Texas Ash Parking Garage
IN CONSTRUCTION
Notes: ICON THEME: Growth
Original $9 M
Rebalance $9.8M
Estimate to complete is the difference between total GO Bond less expenses
Original GMP amount $7,968,892 added $391,351.00
Original GMP approved 12.11.18
SMWVBE: 22%

## Slide 67
NVC – Physical Plant
Project Statistics:
Architect: Alamo Architects
CMAR: SpawGlass Contractors, Inc.
GMP, as amended: $2,798,788
GMP Approved: 12.11.18, Amended on 10.22.19
Building Square Footage: N/A
Construction Start: October 2019
Target Completion: July 2020
Construction % Complete: 70%
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$2.80M | $- | $- | $2.80M | $1.69M | $1.11M
IN CONSTRUCTION
Current scope covers no expansion to building/equipment, only utility connections from plant to new buildings.
Notes: ICON THEME: Growth
Original $3 M
Rebalance $2.8M
Estimate to complete is the difference between total GO Bond less expenses.
Original GMP amount $2,700,000 deducting $(322,832.00)
Original GMP approve date 12.11.18
CMAR SMWVBE % Committed: 25%
SMWVBE: 19%

## Slide 68
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$33.90M | $- | $- | $33.90M | $1.48M | $32.42M
GMP Approved
Project Statistics:
Architect: Overland Partners
CMAR: SpawGlass Contractors, Inc.
GMP: $24,519,433
GMP Approved: 03.17.2020
Building Square Footage: 53,044 sf (3 Stories)
Classrooms: 17 Classrooms
Labs: 7 Labs -Physics, Genetics, Chemistry;
Tutoring – 1 Room
Est. Construction Start: June 2020
Est. Target Completion: September 2021
Est. Academic Term Opening: Fall 2021
CMAR SMWVBE % Committed: 25%
Construction % Complete: GMP Approved
NVC – STEM Center of Excellence
Notes: ICON THEME: STEM LABS; Growth
Original $30M
Rebalance $33.9
SMWVBE: %

## Slide 69
NVC Campus
STEM Site Plan
NVC – STEM Center of Excellence

## Slide 70
East Aerial View
North Aerial View
NVC – STEM Center of Excellence
GMP Approved

## Slide 71
2nd Floor Atrium Rendering
1st Floor Lobby Rendering
GMP Approved
NVC – STEM Center of Excellence

## Slide 72
2nd Level Student Lounge
Student Lounge
Tutoring Center
Dean’s Suite
NVC – STEM Center of Excellence
GMP Approved

## Slide 73
3rd Level Collaborative Space
Study Spaces
Faculty Suite
NVC – STEM Center of Excellence
GMP Approved

## Slide 74
Future
Project Statistics:
Architect: Overland Partners
CMAR: SpawGlass Contractors, Inc.
GMP:
GMP Approved:
Building Square Footage:
Est. Target Completion: Pending GMP
Classrooms and Labs: Classrooms,
Cultural Center. Labs: Archeology and Geography
Est. Target Construction Start: Pending GMP
Est. Target Completion: Pending GMP
Est. Academic Term Opening: Pending GMP
CMAR WMBVBE % Committed: 25%
Construction Complete: Pending GMP
NVC – Cypress Cultural Center of Excellence Renov.
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$4.67M | $- | $8.18M | $12.85M | $0.29M | $12.56M
Notes: ICON THEME: Student Support; Growth
Original $30M
Rebalance $33.9
SMWVBE: %

## Slide 75: Palo Alto College
Dr. Robert Garza, President

## Slide 76
G.O. Bonds (per Election Flyer): $66 Million
COSA Bonds –approx. 49% Natatorium $ 5.3 Million
Maintenance Tax Notes (approved 5/2019) $ 9.8 Million (Gym/Nat. Renovation)
New Multi-purpose Bldg:
Adv. Manuf./Public Service
Welcome Ctr
Defer Palomino Renov./ Healthcare in Multi-purpose Bldg.
Defer lab renov./ Added Labs in Multi-Purpose Bldg.
Joint w/ COSA

## Slide 77
** The four separate projects are proposed to be combined into one new Multi-Purpose Building to allow for great efficiencies including new science labs (rather than renovating the existing Science building) and new dental program (rather than renovating Palomino for healthcare programs).
PAC Updated Budget Targets With MTN Impact
Currently Value Engineering to be within budget
Currently Value Engineering to be within budget
Currently out for bid

## Slide 78
List of Projects
Palo Alto College – Multipurpose Building
Natatorium & Gym Renov. *July 2020
Multipurpose Building (Est. Aug.)
Physical Plant Improvements Renov. (Est. Sept.)
GMP Within Three Months (3)
College Campus | Orig. GO Bond | Allocation Of MTN | Other Funding | Revised GO Bond Plan | Total
PAC | $71.30M | $9.80M | $1.97M | $71.30M | $83.07M

## Slide 79: Site Map
PAC – Master Site Plan

## Slide 80
PAC – Natatorium & Gym Renov.
Project Statistics:
Architect: RVK Architects/Lopez Salas Architects
CMAR: Bartlett Cocke General Contractors
GMP: $
GMP Approved:
Building Square Footage: 90,334 sf (approx.)
Building Upgrades: New Exterior Finishes; Roof Profile and Panels; LED Lighting; Fire Sprinkler System; Interior Finishes; Tile Pool Surface Area. Upgrade Dressing Rooms, Showers and Restrooms Refurbish Diving Platforms
Est. Target Construction Start: *July 2020
Est. Target Completion:
Est. Academic Term Opening: Spring 2022
CMAR SMWVBE % Committed: 40%
Construction % Complete: Pending GMP
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$4.7M | $5.3M CoSA | $9.80M | $19.82M | $1.15M | $18.67M
GMP within 3 Months
Notes: ICON THEME: Growth
Original $8.3 +5.7 =$14M
Rebalance $4.7M
SMWVBE: %

## Slide 81
PAC – Natatorium Renovation
CoSA Interlocal Funding Agreement
Interlocal Funding Agreement:
Details CoSA Financial contribution and Outlines Proportionate expenditures for Maintenance & Capital Improvements
  Total Natatorium Funding: $11M
  CoSA Committed Funding $5,194,000
    $106,000 Admin Cost (kept by CoSA)
  ACD Committed Funding $5.7 M
Percentage Ownership: 49% CoSA / 51% ACD
  Pursuant to a Financing and Joint Use Agreement dated May 17, 1989
May 6, 2017 Election Bonds: Included funds for renovation of the Natatorium in their respective Districts.
GMP within 3 Months
Notes: Add a minute order slide about the PAC CoSA funding agreement within the presentation
CoSA did bond same time as we did
59/41 % ownership
Funding agreement is the joint funding for construction
When was nata built? 1988 --------Mid 90’s had Olympic and used the Nat.
Need ACD board approval prior to CoSA Council Meeting
Add add’l MO for COSA funding agreement for Natatorium

## Slide 82
Southwest Elevation
New Exterior finishes * New roof profile * New Roof Panels * Upgrade dressing rooms, showers & restrooms * New tile at pool surface area * Refurbish diving platforms * New LED lighting * New Fire Sprinkler System * New interior finishes
PAC – Natatorium & Gym Renov.
GMP within 3 Months

## Slide 83
Renovation Improvement Upgrades
Installation of a new fire sprinkler system.
Installation of a new air and ventilation materials and equipment.
Upgrade I.T. cabling and equipment.
Upgrade automation controls.
New LED Lighting and related electrical upgrades
Window repair or replacement as required to make the building more energy efficient.
New metal roof, skylights and new fall protection system.
Natatorium/Gym - Lobby
PAC – Natatorium & Gym Renov.
GMP within 3 Months

## Slide 84
PAC – Multipurpose Building
Project Statistics:
Architect: RVK Architects/Lopez Salas Architects
CMAR: Bartlett Cocke General Contractors
GMP: $
GMP Approved:
Building Square Footage: 128,000 sf (approx.)
Classrooms and Labs: Advance Manufacturing Center, Labs; Public Service Center; Student Engagement & Welcome Center; Healthcare Technology Center of Excellence; Dental Clinic for Community Use; Cyber Security Lab; Science Labs; Simulated Courtroom. Labs: Geology, Physics Biochemistry, Chemistry
Est. Target Construction Start: August 2020
Est. Target Completion: July 2022
Est. Academic Term Opening: Fall 2022
CMAR SMWVBE % Committed: 40%
Construction % Complete: Pending GMP
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$57.78M | $1.97M | $- | $59.75M | $1.55M | $58.19M
GMP within 3 Months
Notes: ICON THEME: Health /Bioscience; Student Support; Information Technology; and Growth
Original $49M
Rebalance $57.7
SMWVBE: %

## Slide 85
West Elevation - Entry
South Elevation
PAC – Multipurpose Building
GMP within 3 Months

## Slide 86
Corridor West Entry
PAC – Multipurpose Building
Lobby Area
West Elevation - Entry
GMP within 3 Months

## Slide 87
PAC – Physical Plant Renov.
Project Statistics:
Architect: RVK Architects/Lopez Salas Architects
CMAR: Bartlett Cocke General Contractors
GMP: $
GMP Approved:
Building Square Footage: 2,800 sf (approx.)
Building Components: Support Mechanical Campus Requirements; 1 New Chiller with Room for Future Additions
Est. Target Construction Start: September 2020
Est. Target Completion: November 2021
CMAR SMWVBE % Committed: 40%
Construction % Complete: Pending GMP
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$3.50M | $- | $- | $3.50M | $3.07M | $3.43M
GMP within 3 Months
Notes: ICON THEME: Growth
Original $3M
Rebalance $3.5M
$11K
SMWVBE: %

## Slide 88: Northeast Lakeview College
Dr. Veronica Garcia, President

## Slide 89
G.O. Bonds (per Election Flyer): $42 Million
Maintenance Tax Notes (approved 5/2019) $8.1 Million (FF&E; add’l NLC Renov.)
Combined
PPI not required

## Slide 90
NLC Updated Budget Targets With MTN Impact

## Slide 91
List of Projects
STEM Science and Technology Building Center of Excellence (Est. Sept.)
  Physical Plant (combined/not required)
Future (1)
Northeast Lakeview College – STEM Building
College Campus | Orig. GO Bond | Allocation Of MTN | Other Funding | Revised GO Bond Plan | Total
NLC | $42.0M | $8.10M* | $- | $42.0M | $50.10M
*This is the maximum MTN available. MTN use on new buildings is restricted to furniture, fixture and equipment.

## Slide 92
NLC – STEM Science and Technology
Center of Excellence
Project Statistics:
Architect: Ford Powell Carson
CMAR: Turner Construction Co.
GMP: $
GMP Approved:
Building Square Footage: 89,052 sf
Classrooms and Labs: 10 General, 4 Computer, Engineering, 1 Multifunction Room. Labs: Geology, Physics, Biochemistry, Chemistry, Technical
Est. Target Construction Start: September 2020
Est. Target Completion: June 2022
Est. Academic Term Opening: Fall 2022
CMAR SMWVBE % Committed: 30%
Construction % Complete: Pending GMP
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$42.0M | $ | $8.10M* | $50.10M | $1.69M | $48.41M
Future
*This is the maximum MTN available. MTN use on new buildings is restricted to furniture, fixture and equipment.
Notes: ICON THEME: Health/Bioscience; STEM Lab; Student Support; Information Technology; and Growth
Original $40M
Rebalance$42M
SMWVBE: %

## Slide 93
South Courtyard View
East Aerial View
Future
NLC – STEM Science and Technology
Center of Excellence

## Slide 94: Education and Training Center
Xavier Urrutia, Interim VCEWD

## Slide 95
List of Projects
Westside Education and Training Center
I-10 Northwest Education and Training Center (Est. Sept.)
Southside Education and Training Center (Est. Jan 2021.)
Future (2)
Westside Education and Training Center February 2020
GMP Approved (1)
College Campus | Orig. GO Bond | Allocation Of MTN | Other Funding | Revised GO Bond Plan | Total
Education Training Centers | $69.0M | $- | $0.80M | $- | $69.80M

## Slide 96
Westside Education and Training Center (WETC)
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/2020 | ESTIMATE TO COMPLETE
$23.0M | $0.80M | $- | $23.80M | $1.14 | $22.66M
Project Statistics:
Architect: HKS
CMAR: Joeris General Contractors
GMP: $18,500,000
GMP Approved: Feb 18, 2020
Building Square Footage: 46,907 sf
Classrooms and Labs: Veterans Outreach, Student Collaboration Areas, Digital Library, Testing Center. Labs: Nanotech Lab, Water Resource Lab, Chemistry Lab Biology Lab (Shell)
Est. Target Construction Start: *Pending Land Purchase (LP)
Est. Target Completion:
Est. Academic Term Opening:
CMAR SMWVBE % Committed: 35%
Construction % Complete: Pending LP
GMP Approved
Notes: ICON THEME: Health/ Bioscience; Student Support; and Growth
Original $23M
Cosa $500K
Veterans $300K
Need from Jennifer..
$843K
SMWVBE: %

## Slide 97
Westside Education & Training Center (WETC)
West Aerial View
South Aerial View
GMP Approved

## Slide 98
Westside Education & Training Center (WETC)
Main Entry
GMP Approved

## Slide 99
Westside Education & Training Center (WETC)
Building “A” Lobby/Learning Stair
Building “B” Learning Stair Level 2
GMP Approved

## Slide 100
Westside Education & Training Center (WETC)
Building “A” Digital Library
GMP Approved

## Slide 101
Northwest Education and Training Center (NWETC)
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$23.0M | - | - | $23.0M | $1.18M | $21.82M
Project Statistics:
Architect: Overland Partners
CMAR: Sundt Construction, Inc.
GMP: $
GMP Approved:
Building Square Footage: 42,000 sf
Classrooms and Labs: General Classrooms, Computer, Technical, Cyber-Tech, Tutorial. Labs: Biology and Chemistry
Est. Target Construction Start: Sept 2020
Est. Target Completion:
Est. Academic Term Opening: Spring 2022
CMAR SMWVBE % Committed: 22%
Construction % Complete: Pending GMP
Future
Notes: ICON THEME: Health/Bioscience; Information Technology; and Growth
Original
$Get expenses from Jennifer/Carol
$463K
SMWVBE: %

## Slide 102
Northwest Education & Training Center (NWETC)
First Floor Plan
Second Floor Plan
Future

## Slide 103
Southside Education and Training Center (SETC)
G.O. BONDS | OTHER FUNDS | MAINTENANCE TAX NOTES | TOTAL FUNDING | EXPENSES THROUGH 6/18/20 | ESTIMATE TO COMPLETE
$23.0M | - | - | $23.0M | $0.61 | $22.39M
Project Statistics:
Architect: Lake Flato
CMAR: Thomas S. Byrne dba Bryne Const. Serv.
GMP: $
GMP Approved:
Building Square Footage: 53,716 sf
Classrooms and Labs: Biblotech, Training Rooms, Robotics, Multipurpose Room, AMT, Allied Health, Nursing spaces, Faculty Office, Conference Room. Labs: Computer Labs, Classrooms, Skills/SIM Lab
Est. Target Construction Start: January 2021
Est. Target Completion:
Est. Academic Term Opening: Fall 2022
CMAR SMWVBE % Committed: 30%
Construction % Complete: Pending GMP
Future
Notes: ICON THEME: Health/Bioscience; Advanced Manufacturing; and Growth
Check with Jennifer and Carol
$50K
SMWVBE: %

## Slide 104
SETC – Site Plan
Future

## Slide 105
SETC – Schematic Floor Plan
Future

## Slide 106
SETC – Schematic Exterior View
Future

## Slide 107
SETC – Schematic Exterior Views
Future

## Slide 108
SETC – Interior Schematics
Future

## Slide 109: CIP Technology Investments

## Slide 110: Technology Domains
Investment Area | Approved Budget
Infrastructure and ACOL | $11,600,000
Instructional Technology | $1,500,000
Communication/Collaboration Tools | $4,100,000
Reporting and Analytics | $1,700,000
Mobile Technology and Security | $6,100,000
 | $25,000,000

## Slide 111: Infrastructure and ACOL
Project | Investment as of June 2020
Switch Refresh | $2,877,530
Storage Upgrade | $596,102
Wireless Refresh / Expansion | $322,373
UPS Refresh | $380,517
ERP Platform Upgrade | $285,041
 | $4,461,563

## Slide 112: Instructional Technology
Project | Investment as of June 2020
iPad Mobile Labs | $142,755
Charging Stations | $248,682
VDI Refresh / Expansion | $398,719
 | $790,156

## Slide 113: Communication / Collaboration Tools
Project | Investment as of June 2020
Alamo Cloud & Security Initiative | $2,503,157
Unified Communications: VOIP Refresh | $561,847
 | $3,065,004

## Slide 114: Reporting and Analytics
Project | Investment as of June 2020
Data Warehouse | $0
Business Intelligence Tools | $0

## Slide 115: Mobile Technology and Security
Project | Investment as of June 2020
Data Vault | $1,351,208
Laptops: Students | $1,217,700
Laptops: Employees | $1,115,542
 | $3,684,450

## Slide 116: Investment Summary
Investment | Approved Budget | Investment as of June 2020
Infrastructure and ACOL | $11,600,000 | $4,461,563
Instructional Technology | $1,500,000 | $790,156
Communication/Collaboration Tools | $4,100,000 | $3,065,004
Reporting and Analytics | $1,700,000 | $0
Mobile Technology and Security | $6,100,000 | $3,684,450
 | $25,000,000 | $12,001,173

## Slide 117: Projects Under Review / In Flight
Project | Potential Investment
Digital Signage | $1,200,000
VDI Refresh / Expansion | $1,500,000
Virtual Reality Classrooms/Labs | TBD
Fiber Linkages | TBD
Firewall Upgrade | TBD
Mobile Apps Strategy | TBD
E-Sports | TBD

## Slide 118: Project Adds, Deletes, Modifications
Project | Potential Investment
Charging Stations & iPad Labs | Add
Student / Employee Laptops | Add
Data Vault | Add
Business Intelligence Tools | Delete
Geolocation Technology | Delete
Digital Signage | Modify

## Slide 120: Construction Manager’s (CMAR) SMWVBE Subcontracting Plans

## Slide 121
Bid/Vender/SMWVBE Management System
Improved Process - One Stop Portal:
Bid opportunities (including other agencies) Vendor Registration
SMWVBE training opportunities Subcontractor payment tracking

## Slide 126: Schedule Next Meeting
Closing Comments

## Slide 127
Thank you

## Slide 128: Appendix

## Slide 129
Citizens Bond Oversight Committee Charge
To accomplish its purpose, the CBOC will:
Determine Committee organizational structure and processes
Meet at least twice per fiscal year
Issue at least 2 written reports to the ACD Board
Monitor the timing and progress of voter approved projects
Review the budget and budget status of the overall bond program and individual projects
Ensure that general contractors seek Better/Builder/Workers Defense Program certification
Monitor diversity utilization including HUB and/or MWBE
Review scope changes in the bond program that may become necessary
Provide input from the community on issues related to the program

## Slide 130
Citizens Bond Oversight Committee
Approved by the ACD Board of Trustees May 15, 2018
Serves in an advisory capacity to the ACD Board
Provides community oversight of the 2017 Bond Program to monitor:
  Efficiency
  Equity
  Timeliness
  Accountability